OPENDEAL

Four-Day Hackathon | Two-Person Task Ownership & Delivery Plan

Team: Chris (Bitcoin settlement / Rust protocol / backend)  •  Olorunshogo (Frontend lead / Rust integration / Bitcoin verification / DevOps)

Planning basis: OpenDeal README, docs/protocol.md, docs/threat-model.md, and docs/roadmap.md reviewed in conversation. Statuses below are repository-roadmap claims, NOT independently tested. Updated 21 October 2026.

# 1. Goal and definition of done

Deliver a reproducible regtest demonstration of a buyer and seller signing an agreement, funding a Bitcoin P2WSH 2-of-3 escrow, confirming funds, releasing payment via external PSBT signatures, and exporting a receipt that independently verifies. Also demonstrate a mediator-assisted refund if stable. Never place participant private keys on the API server.

# 2. Ownership rules

| Area | Accountable owner | Support / handoff |
| --- | --- | --- |
| Rust protocol + signed records | Chris | Olorunshogo reviews Rust API, adds serialization/contract tests and verifies receipts |
| Bitcoin escrow + PSBT + regtest | Chris | Olorunshogo independently tests escrow funding, PSBT outputs, signing and negative cases |
| Axum API + Postgres | Chris | Olorunshogo contributes Axum integration tests and API error handling |
| All Next.js UI/UX | Olorunshogo | Chris supplies API shapes and test fixtures |
| Nostr login UI, session handling | Olorunshogo | Chris verifies API challenge/JWT behavior |
| CI, Compose usability, deployment/demo hosting | Olorunshogo | Chris validates Bitcoin services; both troubleshoot regtest integration |
| Security review + transaction correctness | Chris | Olorunshogo reviews PSBT safety, wallet boundaries, funding verification and user warnings |
| Pitch/demo choreography + final QA | Both | Olorunshogo owns screen recording; Chris owns BTC live flow |

# 3. Complete work inventory — Chris

Legend: Reported done = documented in roadmap, must verify; Pending = documented unfinished; Improve = new task proposed for hackathon quality.

| Task / deliverable | Status | Acceptance criteria / evidence |
| --- | --- | --- |
| Cargo workspace and core crate structure | Reported done | Builds with cargo test --workspace; core public APIs documented. |
| Canonical agreement, dual signatures, deal ID | Reported done | Both signatures verify against same bytes; changed amount fails verification. |
| Deal state machine + invalid transition tests | Reported done | Reject skip-to-funded, skip-to-settled and unauthorized transitions. |
| Hash-chained events and portable receipt verification | Reported done | Receipt validates offline; tampered event fails. |
| P2WSH 2-of-3 address derivation | Reported done | Deterministic output script matches participant pubkeys and network. |
| Funding verification: script, amount, confirmations | Reported done | Wrong script/underpayment/unconfirmed funding rejected. |
| PSBT propose/combine/finalize/broadcast | Reported done | Two external signatures spend escrow; one signature insufficient. |
| Axum endpoints: deals, events, evidence, disputes, receipts | Reported done | Smoke test each endpoint with success + invalid inputs. |
| PostgreSQL schema and persistence | Reported done | Migrations run cleanly; restart preserves deal and event state. |
| Nostr challenge/login and JWT on API mutations | Reported done (API) | Authentication and authorization tests; never trust client actor claims. |
| Idempotency and webhook signatures | Reported done (basic) | Duplicate mutation does not duplicate settlement; invalid webhook HMAC rejected. |
| Live end-to-end regtest wallet/PSBT script | PENDING — critical | Automated 3-wallet demo: fund, mine, verify, sign, broadcast, receipt. |
| Mediator-assisted refund demonstration | Improve — critical | Buyer+mediator co-sign refund PSBT; seller alone cannot spend. |
| PSBT review and fee/output validation | Pending (roadmap Phase 2) | For demo validate recipient, amount, fees, network, change and escrow UTXO. |
| Security tests / threat model review | Improve | Document collusion, frozen funds, replay, confirmations, and recovery limits. |
| API contract / sample requests for frontend | Improve — day 1 | Share endpoint list, payloads, errors, sample deal and receipt JSON. |
| Rust tests, lint, README runbook | Improve | cargo fmt, cargo clippy, cargo test; setup instructions reproducible. |

# 4. Complete work inventory — Olorunshogo

| Task / deliverable | Status | Acceptance criteria / evidence |
| --- | --- | --- |
| Next.js project + landing page | Reported done | Responsive page and correct regtest experimental labeling. |
| Create-deal and deal timeline screens | Reported done | Can create and view deal; state reflects API, not fake UI. |
| Buyer, seller and mediator dashboard views | Reported done (foundation) | Each role sees appropriate actions and state. |
| Mediator desk / dispute screens | Reported done (foundation) | Shows evidence and decision; does not claim decision moves BTC. |
| Frontend dual-sign agreement workflow | PENDING — critical | Both parties review exact agreement hash and sign; invalid signatures rejected. |
| Nostr challenge/login in UI | PENDING | Login via challenge/signature; JWT refresh/logout and protected routes work. |
| Bitcoin funding UI and status polling | Improve — critical | Show address, amount, txid, confirmation count, pending vs confirmed. |
| PSBT external-signing UX | Improve — critical | Present unsigned PSBT, show outputs/fees, import signed PSBT; never collect keys. |
| Payout and mediator refund UI | Improve — critical | Role-aware controls, clear signature requirements and error states. |
| Receipt download and verification UI | Improve | Download JSON; show verification result and tamper-failure demonstration. |
| Typed API client, validation and error handling | Improve | No hardcoded successful responses; loading, retry and errors shown. |
| Frontend integration and E2E tests | Improve | Playwright or equivalent covers deal creation, signing, settlement UI. |
| CI for Rust + frontend | Reported done | Verify clean checkout passes; add E2E job if reliable. |
| Docker Compose developer experience | Reported done | One-command Postgres + bitcoind startup and health checks. |
| Deployment / environment configuration | Pending / improve | Safe public demo UI/API if practical; regtest credentials never exposed. |
| Demo screen recording + presentation assets | PENDING — critical | Backup recording, screenshots, 4-minute narrative, presenter transitions. |
| SEO/favicon/Open Graph polish | Pending — optional | Only after core flow is stable; do not block release. |
| Accessibility, responsiveness and usability QA | Improve | Works on laptop/mobile; warnings readable; keyboard controls functional. |
| Frontend security review | Improve | No secrets in client bundle; avoid XSS, insecure local storage, spoofed state. |
| Rust: Axum API integration and contract tests | NEW — shared technical | Own automated tests for create/accept deal, signature validation, state transitions, receipts, dispute routes and invalid requests; submit Rust PRs. |
| Rust: typed API responses and error consistency | NEW — shared technical | Improve response DTOs, error status codes, OpenAPI examples and frontend-compatible JSON shapes with Chris review. |
| Bitcoin: independently reproduce regtest escrow flow | NEW — critical | Use three Bitcoin Core wallets to verify funding address, amount, confirmations, 2-of-3 signing and successful payout; record TXIDs. |
| Bitcoin: PSBT review and negative tests | NEW — critical | Check PSBT inputs, outputs, fees and network; test one-signature failure, wrong destination, underfunding and unconfirmed funding; no private keys on server. |
| Bitcoin: mediator refund integration test | NEW — critical | Pair with Chris to demonstrate buyer+mediator refund and prove mediator alone cannot spend; capture evidence for judges. |
| Rust: receipt verification CLI / integration checks | NEW — technical | Extend or test offline receipt verifier; prove altered agreement/event invalidates receipt and integrate result in frontend. |

Expanded ownership: Olorunshogo remains responsible for the complete frontend, and also owns Rust API contract tests, independent Bitcoin regtest verification, PSBT safety/negative tests, receipt verifier tests, and joint mediator refund validation. Chris remains accountable for core protocol and settlement implementation. These are additional responsibilities, not a transfer of the entire Bitcoin backend.

# 5. Shared tasks and boundaries

| Task | Primary | Reviewer / rule |
| --- | --- | --- |
| Protocol/API contract freeze (Day 1) | Chris | Olorunshogo signs off on data shapes before frontend integration. |
| Regtest demo setup and sample wallets | Chris | Olorunshogo reproduces steps on own machine or staging. |
| Integration bug triage | Olorunshogo | Chris fixes backend/Bitcoin bugs; Olorunshogo fixes client bugs. |
| Threat-model review | Chris | Both explain mediator collusion, lock-up and no mainnet readiness. |
| README, architecture diagram, installation docs | Olorunshogo | Chris validates Bitcoin and RPC instructions. |
| Live demo script and judging Q&A | Both | Chris explains Bitcoin correctness; Olorunshogo explains UX, integration and extensibility. |
| Final merge / release candidate | Both | No merge without passing tests and one complete live rehearsal. |
| Rust API integration test suite | Olorunshogo | Chris reviews authorization, protocol invariants and merges |
| Independent Bitcoin escrow verification | Olorunshogo | Chris owns escrow implementation; both approve transaction evidence |
| PSBT safety / refund demonstration | Both | Chris builds settlement path; Olorunshogo tests negative cases and signs off |

# 6. Four-day delivery calendar

| Day | Chris — backend / Bitcoin | Olorunshogo — frontend / technical |
| --- | --- | --- |
| 1 — Verify + contracts | Run workspace tests, check RPC/Compose, inspect status, define API payloads; fix blocking core issues. | Run frontend/CI; map user journeys; implement dual-sign UX and typed API client. Write Rust API contract tests; review core agreement serialization. |
| 2 — End-to-end settlement | Implement/run 3-wallet regtest script; escrow funding, confirmation, payout PSBT; negative tests. | Build funding progress, PSBT review/import, role controls; integrate with real API. Independently fund/test escrow on regtest and inspect PSBT outputs and fees. |
| 3 — Dispute + proof | Complete mediator refund, offline receipt verification, state/security tests; support UI integration. | Finish dispute desk, receipt download/verification, Nostr UI; E2E and responsive QA. Pair on mediator refund and tampered-receipt Rust verification tests. |
| 4 — Stabilize + present | Run full regression; fix Bitcoin bugs; rehearse on clean environment; prepare technical Q&A. | Finish CI/demo environment, backup recording, screenshots, pitch visuals; lead end-to-end rehearsal. Run Rust integration suite and Bitcoin negative tests; co-present technical flow. |

# 7. Dependencies and handoff checklist

Day 1 noon: Chris sends API endpoints, request/response examples, error shapes, role permissions, agreement signing bytes and receipt example.

Day 1 end: Olorunshogo demonstrates both-party agreement UX against API or clearly labeled fixtures.

Day 2: Chris delivers a reproducible regtest transaction script and transaction IDs; Olorunshogo wires UI to live funding and signing.

Day 3: Both verify a completed payout, a mediated refund and an intentionally tampered receipt.

Day 4: Freeze features. Fix only blockers; complete live demo and backup recording.

# 8. Demo acceptance checklist

[ ] Fresh checkout and documented commands start database, bitcoind, API and frontend.

[ ] Buyer and seller sign exactly the same canonical agreement; altered terms fail.

[ ] Buyer funds actual regtest 2-of-3 output; wrong address/amount and zero confirmations do not count as funded.

[ ] Buyer + seller sign a PSBT externally and Bitcoin Core broadcasts a valid payout.

[ ] Buyer + mediator demonstrate a refund; mediator alone cannot spend.

[ ] Deal history is consistent with chain events; receipt verifies offline; tampering fails.

[ ] UI never asks for seed phrases/private keys; regtest-only warnings are prominent.

[ ] Demo is repeatable, recorded, and ready to explain within four minutes.

# 9. Explicitly deferred / not required to win the four-day MVP

Do not attempt production mainnet, real user funds, external security audit, automated timelock recovery, real Lightning/fiat settlement adapters, AI dispute adjudication, full observability stack, evidence object storage, email notifications, provider redundancy, rate limits at scale, multi-region ops, or formal dispute SLAs. Keep these in the roadmap and describe them accurately as future work.

# 10. Team decision log (agree before coding)

Agree exact demo scope: payout + mediated refund are the target; receipt tamper proof is mandatory.

Agree whether PSBT signing uses Bitcoin Core wallets or an external signer; no browser private-key storage.

Choose number of confirmations and document it as regtest-only demo policy.

Agree staging URL versus local demo and who controls each environment.

Assign presenters: Chris covers Bitcoin and protocol; Olorunshogo covers user flow, architecture, and open-source integration.

Source: https://github.com/Olorunshogo/OpenDeal  |  Status basis: docs/roadmap.md, README.md, docs/protocol.md, docs/threat-model.md. Implementation claims require test verification.